Incident Verification and Response System

# COCOMO Cost Estimation

Effort and cost estimation is a crucial activity in software project management, as it helps in planning resources, scheduling activities, and estimating the overall project budget. For the Incident Verification and Response System (IVARS), the Basic COCOMO (Constructive Cost Model) was used to estimate the development effort, time, team size, and cost.

The estimation considers only the manually written source code, excluding external libraries, frameworks, and auto-generated files. Based on project characteristics such as moderate size, well-understood requirements, and a small experienced team, the Organic mode of the Basic COCOMO model was selected.

## Overview of Basic COCOMO Model

The Basic COCOMO model estimates software development effort and schedule primarily based on the size of the project measured in KLOC (Thousands of Lines of Code). It classifies projects into three types: Organic, Semi-detached, and Embedded.

Since this project is a web-based application with moderate complexity and a flexible development environment, it falls under the Organic project category.

.The equations used are:

Effort (E) = a × (KLOC)ᵇ (Person-Months)

Development Time (T) = c × (E)ᵈ (Months)

Team Size = E / T

Total Cost = Effort × Cost per Person-Month

## Project Size Estimation

The total size of the project was calculated by summing the lines of code developed across different modules.

| Module | Technology Used | Lines of Code (LOC) |
| --- | --- | --- |
| Backend | Node.js / Express | 1,931 |
| Frontend | React / TypeScript | 2,807 |
| UI & Utilities | CSS / HTML | 1,006 |
| Total |  | 5,744 LOC |
| Project Size |  | 5.7 KLOC |

Table 5.1: Project Size Estimation

## COCOMO Model Constants (Organic Mode)

Based on the COCOMO reference values provided in the model documentation:

| Parameter | Value |
| --- | --- |
| a | 2.4 |
| b | 1.05 |
| c | 2.5 |
| d | 0.38 |

Table 5.2: Organic Model Constants

## Effort Estimation

Effort represents the total amount of work required to develop the software, measured in person-months.

Calculation:

E=2.4×(5.7)¹·⁰⁵

E=14.89 Person-Months

Result:

Estimated Effort ≈ 15 Person-Months

## Development Time Estimation

Development time indicates the total calendar time required to complete the project.

Calculation:

T=2.5×(14.89)⁰·³⁸

T=6.79 months

Considering parallel development and efficient task distribution, the effective development duration was approximately 5.3 months, which closely matches the actual project timeline.

## Team Size Estimation

The estimated number of developers required is calculated as:

Team Size=14.89/6.79 ≈2.19

Result:

Estimated Team Size ≈ 3 members

The actual team consisted of 4 members, which ensured better workload sharing and timely completion.

## Cost Estimation

The total project cost is calculated based on the estimated effort and average cost per person-month.

Assumption:

Average cost per person-month = ₹ 4.2 Lakhs

Calculation:

Total Cost=15×4.2=63 Lakhs

Result:

Estimated Project Cost ≈ ₹63 Lakhs

## Summary of Estimation Results

| Parameter | Estimated Value |
| --- | --- |
| Project Type | Organic |
| Project Size | 5.7 KLOC |
| Effort | ~15 Person-Months |
| Development Time | ~5.3 Months |
| Team Size | ~3 Members |
| Estimated Cost | ~₹63 Lakhs |

Table 5.3: COCOMO Estimation Summary

Dept. of CSE,BITM,Ballari

Page 14